## EHS
EXPLORATORY HOLE SCHEDULE (EHS)
Planned exploratory hole locations issued to the site investigation contractor. Feeds geoCore tables: geotech.site_investigation / geotech.exploratory_hole.
[12 empty] | Summary |  |  | Scheduled | Completed | Precentage | Notes
Project name |  |  | Offshore Wind Farm 1 |  |  |  | project.project_name |  |  |  |  | Total holes scheduled |  |  | 27 | 27 | 100% | Bumpover positions not included in scheduled count
Project code |  |  | OWF01 |  |  |  | project.project_code |  |  |  |  | Total target metres |  |  | 1170 | 1172.7 | 100.2% | Only meterage from holes with status: COMPLETED or ACCEPTED is counted
Site investigation name |  |  | Detailed Design Geotechnical Site Investigation for OWF01 |  |  |  | site_investigation.si_name |  |  |  |  | Exploratory hole (composite) (EH) |  |  | 1 | 1 | 100%
Survey phase code |  |  | GTD |  |  |  | site_investigation.survey_phase_code |  |  |  |  | Boreholes (BH) |  |  | 2 | 2 | 100%
Contractor |  |  | ACME Drilling Ltd. |  |  |  | site_investigation.contractor |  |  |  |  | Grab sample (GS) |  |  | 0 | 0 | #N/A
Layout code / revision |  |  | L002 |  |  |  | project.layout - state layout the cluster/asset refs are planned against, or 'N/A - preliminary/reconnaissance targets' |  |  |  |  | Needle probe (NP) |  |  | 0 | 0 | #N/A
Horizontal CRS (EPSG) |  |  | EPSG:25831 (ETRS89 / UTM 31N) |  |  |  | exploratory_hole.coordinate_system_id - see Appendix 3.F (GIS Manual) and 3.G (Project Reference System Document) |  |  |  |  | Seabed CPTs (CPT) |  |  | 18 | 18 | 100%
Vertical datum (water depths) |  |  | LAT |  |  |  | State vertical datum |  |  |  |  | Downhole CPTs (DCPT) |  |  | 4 | 4 | 100%
Depth reference (hole depths) |  |  | BSF (metres below seafloor) |  |  |  | reference.depth_reference |  |  |  |  | Seabed SCPTs (SCPT) |  |  | 1 | 1 | 100%
Position tolerance |  |  | ± 5 m of target position |  |  |  | Watch circle for hole positioning |  |  |  |  | Downhole SCPTs (SDCPT) |  |  | 1 | 1 | 100%
Bumpover naming convention |  |  | Lowercase suffix a, b, c... appended to hole name |  |  |  | exploratory_hole.bumpover_label
Form revision |  |  | r03 |  |  |  | r**
Date issued |  |  | 2027-09-20 |  |  |  | yyyy-mm-dd
Prepared by |  |  | JONWH
Approved by |  |  | OTHER
Legend: |  |  | Pale blue = cells to complete / edit
No. | Cluster / asset name | Exploratory hole name | Hole type code | Target easting [m] | Target northing [m] | Water depth [m relative to vertical datum] | Target depth [m BSF] | Priority | Position context | Hole status | Start date [yyyymmdd] | End date [yyyymmdd] | As-installed easting [m] | As-installed northing [m] | Final depth [m BSF] | Termination reason | Bumpover label | Bumpover parent hole | Remarks
1 | WTG_001 | CPT-001 | CPT | 496000 | 6155500 | -29.5 | 40 | 1 | ASSET | COMPLETED | 20270903 | 20270903 | 496000.54 | 6155496.74 | 40.1 | TARGET
2 | WTG_002 | CPT-002 | CPT | 499000 | 6156500 | -27.24 | 40 | 1 | ASSET | COMPLETED | 20270903 | 20270903 | 499000.84 | 6156496.33 | 40.1 | TARGET
3 | WTG_003 | CPT-003 | CPT | 502000 | 6156000 | -25.25 | 40 | 1 | ASSET | COMPLETED | 20270903 | 20270903 | 501997.59 | 6156002.66 | 40.1 | TARGET
4 | WTG_004 | CPT-004 | CPT | 505000 | 6154000 | -20.44 | 40 | 1 | ASSET | COMPLETED | 20270903 | 20270904 | 504998.24 | 6153999.76 | 40.1 | TARGET
5 | WTG_005 | CPT-005 | CPT | 495500 | 6151500 | -21.5 | 40 | 1 | ASSET | COMPLETED | 20270904 | 20270904 | 495504.16 | 6151503.97 | 40.1 | TARGET
6 | WTG_006 | CPT-006 | CPT | 499000 | 6152000 | -29.39 | 40 | 1 | ASSET | COMPLETED | 20270904 | 20270904 | 498999.16 | 6151995.03 | 40.1 | TARGET
7 | WTG_007 | CPT-007 | CPT | 503000 | 6151000 | -24.55 | 40 | 1 | ASSET | COMPLETED | 20270904 | 20270904 | 503001.39 | 6151004.66 | 40.1 | TARGET
8 | WTG_008 | CPT-008 | CPT | 506000 | 6149500 | -27.38 | 40 | 1 | ASSET | COMPLETED | 20270905 | 20270905 | 505998.18 | 6149495.63 | 40.1 | TARGET
9 | WTG_009 | BH-009 | BH | 497000 | 6147500 | -28.86 | 50 | 1 | ASSET | COMPLETED | 20270911 | 20270912 | 497003.87 | 6147503.56 | 50.1 | TARGET
10 | WTG_009-A | CPT-009-A | CPT | 497000 | 6147517 | -28.4 | 30 | 1 | ASSET | COMPLETED | 20270905 | 20270905 | 496995.65 | 6147517.6 | 30.1 | TARGET
11 | WTG_009-B | CPT-009-B | CPT | 496985 | 6147491 | -26.7 | 30 | 1 | ASSET | COMPLETED | 20270905 | 20270905 | 496981.29 | 6147492.82 | 30.1 | TARGET
12 | WTG_009-C | CPT-009-C | CPT | 497015 | 6147491 | -20.69 | 30 | 1 | ASSET | COMPLETED | 20270905 | 20270905 | 497013.05 | 6147495.68 | 30.1 | TARGET
13 | WTG_010 | BH-010 | BH | 503500 | 6146500 | -24.63 | 50 | 1 | ASSET | COMPLETED | 20270913 | 20270915 | 503500.97 | 6146497.53 | 50.1 | TARGET
14 | WTG_010-A | CPT-010-A | CPT | 503500 | 6146517 | -26.13 | 30 | 1 | ASSET | COMPLETED | 20270906 | 20270906 | 503496.36 | 6146517.01 | 30.1 | TARGET
15 | WTG_010-B | CPT-010-B | CPT | 503485 | 6146491 | -25.71 | 30 | 1 | ASSET | COMPLETED | 20270906 | 20270906 | 503487.2 | 6146494.58 | 30.1 | TARGET
16 | WTG_010-C | CPT-010-C | CPT | 503515 | 6146491 | -27.85 | 30 | 1 | ASSET | COMPLETED | 20270906 | 20270906 | 503510.3 | 6146490.39 | 30.1 | TARGET
17 | OSS_01 | EH-01 | EH | 501000 | 6149000 | -20.21 | 70 | 1 | ASSET | COMPLETED | 20270915 | 20270917 | 501001.92 | 6148998.55 | 70.1 | TARGET
18 | OSS_01 | SCPT-01 | SCPT | 501000 | 6149000 | -29.69 | 30 | 1 | ASSET | COMPLETED | 20270906 | 20270907 | 501001.37 | 6149001.62 | 30.1 | TARGET
19 | OSS_01 | SDCPT-01 | SDCPT | 501000 | 6149000 | -20.85 | 70 | 1 | ASSET | COMPLETED | 20270909 | 20270909 | 500999.72 | 6149004.11 | 70.1 | TARGET
20 | OSS_01-1 | CPT-01-1 | CPT | 500980 | 6149020 | -24.84 | 30 | 1 | ASSET | COMPLETED | 20270907 | 20270907 | 500976.78 | 6149019.08 | 30.1 | TARGET
21 | OSS_01-1 | DCPT-01-1 | DCPT | 500980 | 6149020 | -22.5 | 70 | 1 | ASSET | COMPLETED | 20270909 | 20270909 | 500975.77 | 6149019.32 | 70.1 | TARGET
22 | OSS_01-2 | CPT-01-2 | CPT | 501020 | 6149020 | -24.6 | 30 | 1 | ASSET | COMPLETED | 20270907 | 20270907 | 501023.37 | 6149019.3 | 30.1 | TARGET
23 | OSS_01-2 | DCPT-01-2 | DCPT | 501020 | 6149020 | -22 | 70 | 1 | ASSET | COMPLETED | 20270909 | 20270910 | 501015.2 | 6149017.66 | 70.1 | TARGET
24 | OSS_01-3 | CPT-01-3 | CPT | 501020 | 6148980 | -26.2 | 30 | 1 | ASSET | COMPLETED | 20270907 | 20270908 | 501023.51 | 6148977.58 | 30.1 | TARGET
25 | OSS_01-3 | DCPT-01-3 | DCPT | 501020 | 6148980 | -22.17 | 70 | 1 | ASSET | COMPLETED | 20270910 | 20270910 | 501019.8 | 6148977.12 | 70.1 | TARGET
26 | OSS_01-4 | CPT-01-4 | CPT | 500980 | 6148980 | -23.38 | 30 | 1 | ASSET | COMPLETED | 20270908 | 20270908 | 500975.44 | 6148981.95 | 30.1 | TARGET
27 | OSS_01-4 | DCPT-01-4 | DCPT | 500980 | 6148980 | -24.42 | 70 | 1 | ASSET | COMPLETED | 20270910 | 20270910 | 500975.73 | 6148978.87 | 70.1 | TARGET

## Guidance
Exploratory Hole Schedule - completion guidance
Purpose
This schedule communicates the planned exploratory hole locations, target depths and naming to the site investigation contractor before mobilisation. It is also a structured input to Ørsted's geoCore databse: the header block populates geotech.site_investigation and the table populates geotech.exploratory_hole (planned fields).
Completing the form
1. Complete every pale-blue cell in the header block. The horizontal CRS must be stated as an EPSG code; coordinates are meaningless without it and geoCore will reject rows lacking a coordinate system.
2. One row per exploratory hole. Co-located holes of different types (e.g. a seabed CPT and a DCPT at the same cluster/asset location) get separate rows, consistent with one geotech.exploratory_hole record per hole.
3. Exploratory hole name is the definitive planned name. The contractor must use it verbatim on field logs and in AGS deliverables (LOCA_ID). Hole number is the structured numeric part, kept as text to preserve leading zeros.
4. Hole type code must be a valid geoCore reference.hole_type code - the cell is validated against the Reference sheet.
5. Water depths are indicative, stated against the vertical datum in the header. Target and minimum acceptable depths are metres below seafloor (BSF).
6. Priority: 1 = must complete; 2 = complete if schedule allows; 3 = contingency/alternate.
Bumpovers and as-completed reporting
If a hole cannot be completed at the target position, relocated attempts are named by appending a lowercase letter (a, b, c...) to the planned name, e.g. HS_S_02_BHa. The contractor shall report as-completed coordinates for every hole (including bumpovers) in the same CRS as this schedule; these populate actual_easting_m / actual_northing_m fields in geoCore.
Termination
A hole is complete when it reaches target depth, or refusal below the minimum acceptable depth. Refusal criteria and any early-termination approvals are governed by the SI contract/specification, which takes precedence over this schedule in case of conflict.
Revision control
Each issue of this schedule increments the form revision (r01, r02...) and is re-approved. The revision in force at mobilisation is the contractual reference; superseded revisions must be clearly withdrawn.

## Reference
Hole type (reference.hole_type) |  | Survey phase (reference.survey_phase) |  | Priority |  | Depth reference (reference.depth_reference) |  | Position context |  | Hole status |  | Termination reason |  | Bumpover label
BH | Borehole | GTP | Geotechnical preliminary | 1 | Primary - must complete | BSF | Below seafloor | ASSET | Hole sited at a physical OWF asset (via layout_asset or asset_location) | SCHEDULED | Planned position, not yet occupied by the vessel/rig | TARGET | Terminated at target depth | a | First bumpover attempt
EH | Exploratory hole (composite) | GTR | Geotechnical reconnaissance | 2 | Secondary - complete if schedule allows |  |  | CLUSTER | Hole belonging to a geotechnical cluster location (geotech.cluster_location) | INPROGRESS | Operations under way at the position | REFUSAL | Refusal above target depth (e.g. cone refusal, spudcan/hard stratum) | b | Second bumpover attempt
GS | Grab sample | GTD | Geotechnical detailed design | 3 | Contingency / alternate position |  |  | STANDALONE | Hole not tied to any asset or cluster (e.g. single seabed CPT in a GTL/GTP campaign) | COMPLETED | Achieved target depth (or contractual acceptance criteria) as planned | EQUIPMENT | Tool, rig or vessel equipment failure | c | Third bumpover attempt
NP | Needle probe | [8 empty] | ACCEPTED | Terminated short of target depth but accepted by the project as complete; no bumpover required | WEATHER | Terminated due to weather or operational downtime | d | Fourth bumpover attempt
CPT | Cone penetration test (seabed mode) | [8 empty] | FAILED | Terminated prematurely (early refusal, equipment failure, tool loss etc.) and not accepted; typically superseded by a bumpover | PROJECT | Terminated or abandoned by project/client instruction | e | Fifth bumpover attempt
DCPT | Downhole CPT | [8 empty] | ABANDONED | Attempted or partially attempted, then abandoned by project decision; will not be completed or bumped over | OTHER | Other reason; see remarks | f | Sixth bumpover attempt
SCPT | Seismic cone penetration test (seabed mode) | [8 empty] | CANCELLED | Removed from the schedule before any attempt was made
SDCPT | Downhole SCPT
VC | Vibrocore
This sheet mirrors geoCore reference tables. Do not edit codes; extend only via a geoCore reference-data change.